## Slide 1: Final Presentation
Team Indigo 20200854 황찬기 / 20210210 이다민 / 20220019 안재영

## Slide 2: Overall progress
Week | Progress
Week 1 | Created Project Repository / Fixed Meeting Plan & Tools to Use
Week 2 | Decided Git Convention / Researched Basic Concepts of Project
Week 3 | Researched about Each Steps for Implementing / Basic Structure Design
Week 4 | Detailed Structure Design
Week 5 | Set gRPC & Basic Scala Project Files on Git
Week 6 | Intermediate Presentation / Reset Project Structure Design
Week 7 | Implemented gRPC / Sampling & Partitioning / Shuffling & Merging Each
Week 8 | Tried to Merge All Implemented Features

## Slide 4: Overall progress
Before Progress Presentation
initial setting → sorting → sampling → partitioning → shuffling → merging
After
initial setting → sampling → sorting & partitioning → shuffling → merging
We changed our roles, according to each phases
  took lots of time by connecting members’ phases

## Slide 5: Overall progress
Role
Member | Role
황찬기 | Initial setting & gRPC Connection
이다민 | Shuffling & Merging
안재영 | Samping & Partitioning

## Slide 6: Final architecture (master & worker)

## Slide 7: How to Run

## Slide 8: Final execution
Successfully Connected Master - Workers
Workers create sample and successfully send it to master
Master calculates key range and successfully send it to worker
We could get some sorted files during the sorting state of worker
Master successfully prints changes of these sorting phases
But after the sorting state is not completed…

## Slide 9: Experiment
We failed to implement complete sorting
  each member tried to implement each part of sorting, but failed to merge & fix bugs
  we ended up at sorting phase (initial setting → sampling → sorting & partitioning → shuffling → merging ( → finish))

## Slide 10: Analysis of Failures
Wasted too much time on trivial things
  After progress presentation, we had to make code but …
No Test Code
  We should have tried to make sample code earlier
Extremely lacking time
  We did not have enough time to get familiar with code
Optimism
  From Mythical Man-Month Ch.2
  We did not consider communication overhead enough
  Merging each part of members was hard

## Slide 11: Lessons learned from the project
Use time more efficiently & Use more time
Run toy code first, then try to get more deeper